## RF
LOGICAL FRAMEWORK TEMPLATE
PROGRAM: | ADMINISTRATION AND FINANCE |  | Review staffing plan and organogram
SUB-PROGRAM: | HR, FINANCE, ADMIN, RESORCE MOBILIZATION AND COMMUNICATION, MONITORING AND EVALUATION
GOAL: | TO ENHANCE ORGANIZATIONAL EFFICIENCY AND EFFECTIVENESS
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Strengthen organizational capacity | Organizational capacity improved | An operational plan developed | Develop operational planning framework | An operational plan developed and functional | Reports, operational plan | Q1 2024 | Planning and Development Team
|  | A communication strategy developed | Develop a communications strategy | A communication strategy developed and operational | Communication materials, surveys | Q2 2024 | Communications Team
|  | A stakeholder mapping and engagement plan developed | Develop a stakeholders’ mapping and engagement plan | A stakeholder mapping and engagement plan developed and operational | Stakeholder mapping report | Q3 2024 | Partnership Team
|  | SOPs developed for organizational processes | Develop Standard Operating Procedures (SOPs) | Number of processes with operational SOPs | SOP manuals, process audits | Q4 2024 | Operations Team
|  | M&E system/ process automated | Procure an M&E data system | Number of M&E reports generated through the M&E data system | M&E system reports | Q1 2025 | M&E and IT Teams
To enhance organizational governance | An organizational governance and succession framework | An organizational governance and succession framework developed and operational | Develop an organizational governance and succession framework | Governance framework document | Governance framework document, compliance audit reports, feedback from stakeholders | Q2 2024 | Governance Team
To enhance staff capacity | Staffing plan and organogram reviewed and implemented | Updated staffing plan and organogram | Review staffing plan and organogram | Staffing reports | Updated organogram, HR records, staffing evaluation report. | Q1 2024 | HR Department
|  | A training and capacity building program developed | Develop training and capacity building program | Number of staff trained | Training attendance records | Ongoing | HR and Training Department
|  | Existing performance management plan fully implemented | Implement the performance management plan | Number of performance management reports shared with management for decision-making | Performance reports | Ongoing | HR & M&E Department
To increase the efficiency in financial management | The financial policies and procedures fully reviewed | Review the financial policies and procedures | The financial policies and procedures fully reviewed and utilized | Policy review reports | Updated financial policies document, internal audit reports, compliance reviews, financial management system updates, training records for finance staff | Q1 2024 | Finance Team
|  | A risk management strategy developed | Develop risk management strategy | A risk management strategy developed and operationalized | Risk assessment reports | Q2 2024 | Risk and Compliance Team
Increase and diversify resources for Caritas Nairobi’s programmes | Increased and sustainable resources for Caritas Nairobi’s programmes | Donor register | Carry out donor mapping | Number of donors in the register | Donor database | Q3 2024 | Fundraising Team
| Enhance international and local fundraising initiatives | International Donor Networking done | Attend international conferences | Number of donor meetings attended | Conference reports | Q4 2024 | External Relations Team
|  | Implement donors’ stewardship (relationship management) | Number of donors retained | Number of retained donors | Retention analysis reports | Ongoing | Donor Relations Team
|  | Hold stakeholders’ forums and fundraising events | Stakeholders’ forums and fundraising events held | Number of stakeholders’ forums organized and conducted | Event reports | Bi-annually | Events and Fundraising Team
|  | Utilize online fundraising platforms | Online fundraising platform utilized | Number of online fundraising platforms established and utilized | Fundraising platform usage data | Q1 2025 | IT and Fundraising Teams
|  | Develop targeted communication materials | Communication Materials Developed | Number of communication materials developed | Marketing records | Ongoing | Communications Team
|  | Develop a funding policy | Funding policy developed | An operational funding policy developed | Policy document | Q2 2024 | Policy Development Team
|  | Develop activities and events for Caritas week | Caritas Nairobi aligned to the ADN Charity mission | Number of activities organized | Event calendars | Annually | Events Team
|  | Develop a concept bank | Program concept bank developed | Number of concept notes developed | Concept bank records | Q3 2024 | Programs Team
|  | Enhance brand visibility | Brand visibility enhanced | Brand visibility index | Brand perception surveys | Ongoing | Marketing and Communications
Enhance income-generating activities | A developed IGA policy | Policy document developed | Establish policies for development and management of IGAs | A functional IGA policy | Approved IGA policy document, internal audit reports. | Q1 2025 | Income Generation Team
| Re-establish Caritas Nairobi family network | Fundraising events held | Hold fundraising events | Number of fundraising events held | Event reports | Ongoing | Fundraising Team
Instructions;
1. Use the strategic plan and operational plan to fill in the information
2. Uder Strategic Objectivendicator, intermediate Outcomes, Outputs, Key indicators, MOV, Time frame and responsibility use the guide provided in each of them
3. Create more rows as may be required

## sample fs RF
Promote
LOGICAL FRAMEWORK TEMPLATE |  |  | sustainable food
PROGRAM: | ADMINISTRATION AND FINANCE |  | production in selected value chains
SUB-PROGRAM:
GOAL: | To enhance living standards, self-reliance and dignity of communities in the Archdiocese of Nairobi
GOAL 2; | TO ENHANCE ENVIRONMENTAL SUSTAINABILITY AND RESILIENCE
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Increase food security, safety and nutrition within communities in the AND | Food security within communities in the ADN increased | Increased knowledge on climate smart farming | Training farmers on climate smart agriculture | Number of trainings held on climate smart agriculture, Number of farmers practicing climate smart farming | Training Reports | countinous | FSE Coordinator
Instructions;
1. Use the strategic plan and operational plan to fill in the information
2. Uder Strategic Objectivendicator, intermediate Outcomes, Outputs, Key indicators, MOV, Time frame and responsibility use the guide provided in each of them
3. Create more rows as may be required

## SAMPLE RF
LOGICAL FRAMEWORK TEMPLATE
PROGRAM: | ADMINISTRATION AND FINANCE
SUB-PROGRAM: | HR, FINANCE, ADMIN, RESORCE MOBILIZATION AND COMMUNICATION, MONITORING AND EVALUATION
GOAL: | TO ENHANCE ORGANIZATIONAL EFFICIENCY AND EFFECTIVENESS
PROJECT DESCRIPTION | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS
Goal: Enhance organizational efficiency and effectiveness | Percentage increase in program impact across all thematic areas | Annual evaluation reports, strategic impact studies | Adequate resources and stakeholder collaboration
Outcomes | Improved organizational capacity | Progress reports, operational audits | Supportive policy environment and staff buy-in
| Enhanced organizational governance | Governance assessment reports | Leadership commitment to governance improvements
| Increased and diversified resources for programs | Donor and funding databases, annual financial reports | Continued donor and stakeholder interest
| Strengthened financial management systems | Financial audit reports | Economic stability and predictable funding streams
| Improved monitoring and evaluation processes | M&E framework reports, automated system data | Availability of functional M&E tools and expertise
| Enhanced communication and brand visibility | Communication campaigns reports and materials developed | Positive public perception and media engagement
Outputs | Operational plan, communication strategy, stakeholder mapping plan | Planning and communication materials, stakeholder engagement logs | Availability of expertise and timely resource allocation
| Fully implemented performance management plan | Performance management reports | Consistent staff engagement
| Increased stakeholder forums and fundraising events | Event reports, participant attendance records | Supportive external networks and partnerships
| Developed M&E framework and automated processes | Framework document, reports generated by automated systems | Functional IT infrastructure for automation
| Streamlined financial procedures and policies | Number of policies reviewed and adopted | Collaboration from finance teams and leadership
| Comprehensive resource mobilization strategy | Number of donor proposals developed and submitted | Donor willingness to support funding priorities
| Improved internal and external communication processes | Communication plans and reports, media coverage | Timely execution of communication strategies
Activities | Develop operational planning framework | Number of planning meetings and workshops held | Operational assumptions remain stable
| Train staff on governance, financial policies, and communication strategies | Training attendance and feedback forms | Willingness of staff to engage in training programs
| Conduct donor mapping, stewardship, and proposal writing | Number of donors identified and retained, number of proposals submitted | Positive donor response to engagement efforts
| Develop targeted communication materials and online platforms | Number of materials produced, usage data for platforms | Access to reliable IT infrastructure
| Automate M&E processes and train staff on using M&E systems | Number of staff trained, automated reports generated | Adequate budget and IT support for M&E systems
| Conduct stakeholder forums and fundraising events | Number of events organized and attendance | Stakeholder commitment to attend and support events

## Sheet2
LOGICAL FRAMEWORK TEMPLATE
PROGRAM: | ADMINISTRATION AND FINANCE
SUB-PROGRAM: | HR, FINANCE, ADMIN, RESORCE MOBILIZATION AND COMMUNICATION, MONITORING AND EVALUATION
GOAL: | TO ENHANCE ORGANIZATIONAL EFFICIENCY AND EFFECTIVENESS
PROJECT DESCRIPTION | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS
Goal: Increase food security, safety and nutrition within communities in the AND | % of the target popultion food secure. | evaluation report, survey reports, local food secirity studies from the government
Outcomes
1.Promote sustainable food production in selected value chains | Number of target families taking 3 meals a day | midterm evaluations, progress reports | That the target population are willing to participate in project intervetion
2.Support food safety and nutrition
1.Promote sustainable food production in selected value chains
Outputs
1.1 Increased knowledge on climate smart farming
1.2 Increased adoption of farming technology
1.3 Increased access to farming knowledge and skills
1.4 Increased knowledge and skills on post-harvest management
2.Support food safety and nutrition
Outputs 2
2.1 Farmers gained knowledge on food safety and food hygiene
2.2 Improved understanding of nutrition and dietary practices among the community
Kitchen gardens for fresh and nutritious produce established
Adoption of organic farming increased