## RF G1 OB 1
LOGICAL FRAMEWORK TEMPLATE
|  |  | PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
|  |  | GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
[High-level objective] | [Mid-term achievements] | [Specific deliverables] | [Tasks or processes to achieve outputs] | [Quantitative/qualitative indicators] | [Reports, surveys, interviews] | [Dates/deadlines] | [Assigned team/department]
Increase income levels and financial resilience of vulnerable communities within the ADN | Income levels of vulnerable communities within ADN increased | Increased knowledge and skills in entrepreneurs hip | Conduct training on entrepreneurship | Number of target community members with increased knowledge and skills in entrepreneurship | 1. Pre and post-training evaluation reports 2. Survey Reports | Quarterly | SEEP CBM
|  |  |  | Number of training sessions conducted successfully | 1. Training reports | Quarterly | SEEP CBM
|  | Community- based business and incubation centers established | Establish community- based business mentorship and incubation centers | Number of community- based business incubation centers established and functional. | 1. Photographic and video evidence 2. Ownership Agreement contracts | 2025-09-01 | SEEP CBM
|  | Enhanced business linkages and collaboration. | Establish partnerships and collaboration for local organizations to create job opportunities. | Number of linkages established. | 1. Partnership Agreement Contracts | Semi-annually | SEEPC
|  |  |  | Number of job opportunities created as a result of the linkages. | 1. lists of people hired | Semi-annually | SEEPC
|  | Increased number of market linkages | Create market linkages for local communities | Number of local community groups and individuals linked to market opportunities
Amount of revenue generated from the linkages
|  | Increased knowledge in financial literacy | Conduct financial literacy training for the target community | Number of people with increased knowledge in financial literacy | 1. Pre and post-training evaluation reports 2. Survey Reports | Quarterly | SEEP CBM
|  |  |  | Number of training sessions conducted successfully | 1. Training reports | Quarterly | SEEP CBM
|  | Increased use of digital banking platforms | Promote the use of digital banking platforms for transactions | Number of people using digital banking platforms | 1. Transaction Logs | Monthly | ICT & Innovation
|  | Innovative financial products and services developed | Develop innovative financial products and services | Number of innovative financial products and services developed | 1. Product Profile | Annually | ICT & Innovation
|  | Innovative financial products and services adopted |  | The number of people consuming the newly developed financial products and services | 1. System Products Reports | Monthly | ICT & Innovation
|  | Capacity of community savings groups enhanced | Enhance capacity of community- based savings groups | Number of communities saving groups with enhanced capacity | 1. Pre and post-training evaluation reports 2. Survey Reports 3.Financial Reports 4. Management Reports | Quarterly | SEEP CBM
|  | Increased micro- enterprises targeting women and youth. | Promote formation of micro- enterprises targeting women and youth | Number of micro- enterprises targeting women and youth formed | 1. Registration certificates 2. Photographic and video evidence | Quarterly | SEEPC
Instructions;
1. Use the strategic plan and operational plan to fill in the information
2. Uder Strategic Objectivendicator, intermediate Outcomes, Outputs, Key indicators, MOV, Time frame and responsibility use the guide provided in each of them
3. Create more rows as may be required

## G1 OBJ 3
LOGICAL FRAMEWORK TEMPLATE
|  |  | PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
|  |  | GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
To enhance relief services within the AND | Social wellbeing of the target population improved | Increased knowledge on business skills and mentorship | Training on business skills and mentorship to the vulnerable groups | Number of participants completing training | 1. Pre and post-training evaluation reports 2. Training Reports | Semi-Annually (align with relief program training calendar) | SEEP CBM

## G1 OBJ 4
LOGICAL FRAMEWORK TEMPLATE
|  |  | PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
|  |  | GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Enhance the institutional capacity and sustainability of community-based institutions under the ADN | Operations of the CBIs improved | Capacity gap assessment s undertaken for each CBI | Assessment of capacity gaps | Number of CBIs with completed capacity gap assessments reports | 1. Gap analyses reports 2. Survey reports (questionnaires) | Quarterly | SEEP CBM
|  | Business management knowledge and skills among CBI staff increased | Training on business management | Number of CBI staff trained in business management topics (e.g., budgeting, marketing). | 1. Training reports | Quarterly | SEEP CBM
|  |  |  | Number of CBI staff with increased knowledge on business management topics (e.g., budgeting, marketing). | 1. Pre and post-training evaluation reports 2. Survey Reports | Quarterly | SEEP CBM
|  | Delivery of training programs on governance and leadership for CBI boards and staff. | Training on governance and leadership | Number of CBIs participating in governance and leadership training programs. | 1. Training reports | Quarterly | SEEP CBM
|  |  |  | Number of board members and staff trained in good governance practices. | 1. Training reports | Quarterly | SEEP CBM
|  |  |  | Improved scores on board effectiveness assessments | 1. Board evaluation and performance reports | Quarterly | SEEP CBM
|  | Increased awareness of diverse funding sources among CBI staff (surveys or interviews). | Sensitization on resource mobilization | Number of CBIs participating in resource mobilization workshops or seminars. | 1. Training reports | Annually | RMP
|  |  |  | Number of grant proposals submitted by CBIs (after training). | 1. Concept Papers 2. Proposals repository | Semi-Annually | RMP
|  | Improved systems and structures within CBIs (e.g., financial management systems, monitoring and evaluation frameworks). | Establishment of systems and structures | Number of CBIs with documented and implemented financial management systems | 1. Policies 2. SOPs | Annually | SEEPC
|  |  |  | Number of CBIs with established monitoring and evaluation frameworks. | 1. M&E reports | Annually | SEEPC and M&E
|  |  |  | Number of CBIs using established financial management systems and monitoring and evaluation frameworks in day-to-day operations (e.g., reports generated). | 1. Policies 2. SOPs 3. M&E Reports | Annually | SEEPC and M&E
|  | A platform or mechanism for CBIs to facilitate network and collaborate (e.g., online forum, workshops) established and operationalize d | Establish a platform/ mechanism to facilitate networking and collaboration | Number of CBIs actively participating in the networking platform. | 1. Attendance registers 2. Photographic and video evidence | Semi-Annually | SEEPC
|  |  |  | Number of collaborations between CBIs on projects or initiatives (documented examples) | 1. Collaborative initiatives | Semi-Annually | SEEPC

## G2 OBJ 1
LOGICAL FRAMEWORK TEMPLATE
|  |  | PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
|  |  | GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Promote sustainable land management and conservation within the ADN by 2028 | Land and forest degradation within the ADN reduced | A tree growing program established | Establish a tree growing program | Number of trees grown | 1. Photographic and video evidence 2. Tree growing initiative reports | Annually | SEEPC
|  |  |  | Number of partnerships formed towards tree growing e.g. research centres | 1. Partnership Agreement Contracts | Annually | SEEPC
|  |  |  | Number of awareness forums held on tree growing | 1. Photographic and video evidence 2. Attendance registers | Semi-Annually | SEEPC
|  |  |  | Number of tree seedlings produced | 1. Tree nurseries | Annually | Food Security Dpt
|  | Awareness on renewable energy sources and technologies increased | Raise awareness on renewable energy sources and technologies | Number of promotion forums held | 1. Promotion Reports | Quarterly | SEEPC
|  | Renewable energy sources and technologies adopted | Provide access to renewable energy sources and technologies | Number of Households adopting the use of renewable energy sources and technologies | 1. Uptake of green loans | Monthly | SEEPC
|  | Training and sensitization forums of farmers on soil conservation practices held | Training and sensitization of farmers on soil conservation practices and organic farming | Number of trained farmers | 1. Photographic and video evidence 2. Attendance registers | Quarterly | SEEPC CBM
|  |  |  | Number of trainings held | 1. Training reports | Quarterly | SEEPC CBM
|  | Demo farms for training on best land management practices established | Establishing demo farms for training on best land management practices | Number of demo farms established

## G2 OBJ 2
LOGICAL FRAMEWORK TEMPLATE
|  |  | PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
|  |  | GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Promote sustainable waste management within ADN | Waste pollution within ADN reduced | Enhanced knowledge on recycling. | Sensitization on recycling | Number of people and sensitization meetings conducted on recycling | 1. Photographic and video evidence 2. Attendance registers | Quaterly | SEEPC
|  | Community based Recycling Centres established. | Pilot waste recycling centres | Number of community based recycling of waste . | 1. Photographic and video evidence 2. Ownership Agreement contracts | Annually | SEEPC
|  | Innovations and enterprises in waste value chain improved. | Support innovations and enterprises in waste value chain | Number of innovations and enterprises in waste value chain supported. | 1.Partnership Agreement Contracts | Annually | SEEPC
|  | Community clean up services undertaken. | Carry out community clean-up activities | Number of community clean-up activities conducted. | 1. Photographic and video evidence | Annually | SEEPC

## G3 OBJ 1
LOGICAL FRAMEWORK TEMPLATE
PROGRAM:
SUB-PROGRAM:
GOAL:
Strategic Objective | Intermediate Outcomes | Outputs | Key Activities | Indicators | Means of Verification | Timeframe | Responsibility
Strengthen organizational Capacity | Organizational capacity improved | A training and capacity building program developed | Develop training and capacity building program | No. of staff trained | 1. Training reports 2. Training Calendar 3. Budgets | Annually | SEEP CBM
|  | A risk management strategy developed | Develop risk management strategy | A risk management strategy developed and operationalized | 1. Risk monitoring & evaluation reports | Monthly | RCO

## LF G1 OB 1 Log Frame
LOGICAL FRAMEWORK TEMPLATE
PROGRAM: | Socio-Economic Empowerment Programme
SUB-PROGRAM:
GOAL: | To enhance living standards, self-reliance and dignity of communities in the AND
PROJECT DESCRIPTION | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS
Goal:
To enhance living standards, self-reliance and dignity of communities in the AND
Outcomes
Income levels of vulnerable communities within ADN increased
Outputs
Increased knowledge and skills in entrepreneurs hip
Community- based business and incubation centers established
Enhanced business linkages and collaboration.
Increased number of market linkages
Increased knowledge in financial literacy
Increased use of digital banking platforms
Innovative financial products and services developed
Capacity of community savings groups enhanced
Increased micro- enterprises targeting women and youth.
Activities
Establish community- based business mentorship and incubation centers
Establish partnerships and collaboration for local organizations to create job opportunities.
Create market linkages for local communities
Conduct financial literacy training for the target community
Promote the use of digital banking platforms for transactions
Develop innovative financial products and services
Enhance capacity of community- based savings groups
Promote formation of micro- enterprises targeting women and youth

## GUIDE
LOGICAL FRAMEWORK TEMPLATE
PROGRAM:
SUB-PROGRAM:
Project Description | Indicators | Means of Verification | Assumptions
Goal | [Impact indicators] | [Evaluation reports, studies] | [Conditions for achieving the goal]
To enhance living standards, self-reliance, and dignity of communities in the ADN
Outcomes | [Outcome indicators] | [Baseline/endline data, assessments] | [External factors affecting outcomes]
Outputs | [Output indicators] | [Activity reports, attendance] | [Resources, capacity to deliver outputs]
Activities | [Process indicators] | [Monitoring forms, logbooks] | [Operational assumptions, risks]
Instructions;
1. Use the strategic plan and operational plan to fill in the information
2. Uder indicator MOV and Assumptions use the guide provided in each of them
3. Create more rows as may be required